## IBDS1 flow
Summary | Story Points | Assignee | Reporter | Sprint | Epic Link | Issue Type | Project Name | Sprint_Board | Sprint_Id | Project Key | Acceptance Criteria
<CDS IBDS1.0 Feature A> - Requirement (Technical Design & Test Plan) | 3 | cheahchr | seanyitl | 2023.R1.2w.S1 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S1 TWC3149 | 181686 | TWC3149 | Finalize LDM with DA Complete PDM readiness
<CDS IBDS1.0 Feature A> - Create PDM and Wiki | 3 | cheahchr | seanyitl | 2023.R1.2w.S1 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S1 TWC3149 | 181686 | TWC3149 | Mapping document, technical design, PDM, WIKI, test plan published and reviewed
<CDS IBDS1.0 Feature A> - ETL Configuration - Dev | 2 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S2 TWC3149 | 181695 | TWC3149 | ETL run sccessfully without error
<CDS IBDS1.0 Feature A> - ETL Configuration - QA | 1 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S2 TWC3149 | 181695 | TWC3149 | ETL run sccessfully without error
<CDS IBDS1.0 Feature A> - DB Development | 3 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S2 TWC4618 | 181346 | TWC4618 | DB development completed and tested without error
<CDS IBDS1.0 Feature A> - DB QA migration | 2 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S2 TWC4618 | 181346 | TWC4618 | QA migration completed successfully Query view on selected rows returns valid data
<CDS IBDS1.0 Feature A> - Mulesoft Development | 3 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S2 TWC3149 | 181695 | TWC3149 | API development completed and tested without error
<CDS IBDS1.0 Feature A> - Mulesoft QA Migration | 1 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S2 TWC3149 | 181695 | TWC3149 | QA migration completed successfully Query API returns valid data
<CDS IBDS1.0 Feature A> - Denodo/APIGee Development | 3 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S2 TWC4618 | 181346 | TWC4618 | Complete API development and unit testing
<CDS IBDS1.0 Feature A> - Denodo/APIGee QA Migration | 1 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S2 TWC4618 | 181346 | TWC4618 | QA migration completed successfully Query API returns valid data
<CDS IBDS1.0 Feature A> - Dev Functional Testing | 2 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S2 TWC4618 | 181346 | TWC4618 | Complete functional testing with sample data
<CDS IBDS1.0 Feature A> - Batch Job Creation - Dev | 1 | cheahchr | seanyitl | 2023.R1.2w.S3 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S3 TWC3149 | 181705 | TWC3149 | Batch job run successfully Query view on refreshed rows returns valid data
<CDS IBDS1.0 Feature A> - Batch Job Creation - QA | 1 | cheahchr | seanyitl | 2023.R1.2w.S3 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S3 TWC3149 | 181705 | TWC3149 | Batch job run successfully Query view on refreshed rows returns valid data
<CDS IBDS1.0 Feature A> - QA Functional Testing | 1 | cheahchr | seanyitl | 2023.R1.2w.S3 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S3 TWC3149 | 181705 | TWC3149 | New/updated features work as per specification without impacting existing business scenario. Test cases and results documented and tracked in JIRA
<CDS IBDS1.0 Feature A> - DB Prod Migration | 2 | cheahchr | seanyitl | 2023.R1.2w.S4 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S4 TWC4618 | 181366 | TWC4618 | Prod migration completed successfully Query view on selected rows returns valid data
<CDS IBDS1.0 Feature A> - Mulesoft Prod Migration | 1 | cheahchr | seanyitl | 2023.R1.2w.S4 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S4 TWC3149 | 181707 | TWC3149 | Prod migration completed successfully Query API returns valid data
<CDS IBDS1.0 Feature A> - Denodo/APIGee Prod Migration | 1 | cheahchr | seanyitl | 2023.R1.2w.S4 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S4 TWC4618 | 181366 | TWC4618 | QA migration completed successfully Query API returns valid data
<CDS IBDS1.0 Feature A> - ETL Configuration - Prod | 1 | cheahchr | seanyitl | 2023.R1.2w.S4 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S4 TWC3149 | 181707 | TWC3149 | ETL run sccessfully without error
<CDS IBDS1.0 Feature A> - Batch Job Creation - Prod | 1 | cheahchr | seanyitl | 2023.R1.2w.S4 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S4 TWC3149 | 181707 | TWC3149 | Batch job run successfully Query view on refreshed rows returns valid data

## HANA flow
Summary | Story Points | Assignee | Reporter | Sprint | Epic Link | Issue Type | Project Name | Sprint_Board | Sprint_Id | Project Key | Acceptance Criteria
<CDS HANA Feature A> - Requirement | 3 | cheahchr | seanyitl | 2023.R1.2w.S1 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S1 TWC3149 | 181686 | TWC3149 | Finalize LDM with DA Complete PDM readiness
<CDS HANA Feature A> - Create Mapping Document, PDM and Wiki | 5 | cheahchr | seanyitl | 2023.R1.2w.S1 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S1 TWC3149 | 181686 | TWC3149 | Complete Mapping document, technical design, PDM, WIKI, test plan
<CDS HANA Feature A> - DS Job Technical Design | 2 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S2 TWC3149 | 181695 | TWC3149 | Complete ETL design document
<CDS HANA Feature A> - DS Job Development | 3 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S2 TWC4618 | 181346 | TWC4618 | DS job setup and tested running successfully Source tables visible in HANA New tables created
<CDS HANA Feature A> - DS Job Review and Testing | 1 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S2 TWC4618 | 181346 | TWC4618 | DS job setup and tested running successfully Source tables visible in HANA New tables created
<CDS HANA Feature A> - DS Job QA Migration | 1 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S2 TWC4618 | 181346 | TWC4618 | QA migration completed successfully
<CDS HANA Feature A> - HANA View Development | 3 | cheahchr | seanyitl | 2023.R1.2w.S2 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S2 TWC4618 | 181346 | TWC4618 | A,B,C,D view created/updated as per design document Validate changes made not impacting other views Query view on selected rows returns valid data
<CDS HANA Feature A> - HANA QA Migration | 2 | cheahchr | seanyitl | 2023.R1.2w.S3 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S3 TWC4618 | 181352 | TWC4618 | QA migration completed successfully Query view on selected rows returns valid data
<CDS HANA Feature A> - HANA QA Code Review | 1 | cheahchr | seanyitl | 2023.R1.2w.S3 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S3 TWC4618 | 181352 | TWC4618 | HANA Code developed as per IT standard
<CDS HANA Feature A> - Batch Job Creation - QA | 1 | cheahchr | seanyitl | 2023.R1.2w.S3 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S3 TWC4618 | 181352 | TWC4618 | Batch run successfully Query view on refreshed rows returns valid data
<CDS HANA Feature A> - HANA QA Functional Testing | 1 | cheahchr | seanyitl | 2023.R1.2w.S3 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S3 TWC3149 | 181705 | TWC3149 | New/updated features work as per specification without impacting existing business scenario. Test cases and results documented and tracked in JIRA
<CDS HANA Feature A> - Denodo/APIGee development | 3 | cheahchr | seanyitl | 2023.R1.2w.S3 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S3 TWC4618 | 181352 | TWC4618 | Complete API development and unit testing
<CDS HANA Feature A> - Denodo/APIGee QA Migration | 1 | cheahchr | seanyitl | 2023.R1.2w.S3 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S3 TWC4618 | 181352 | TWC4618 | QA migration completed successfully Query API returns valid data
<CDS HANA Feature A> - DS Job Prod Migration | 1 | cheahchr | seanyitl | 2023.R1.2w.S4 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S4 TWC4618 | 181366 | TWC4618 | Prod migration completed successfully Query view on refreshed rows returns valid data
<CDS HANA Feature A> - Batch Job Creation - Prod | 1 | cheahchr | seanyitl | 2023.R1.2w.S4 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S4 TWC4618 | 181366 | TWC4618 | Batch run successfully Query view on refreshed rows returns valid data
<CDS HANA Feature A> - HANA Prod Migration | 2 | cheahchr | seanyitl | 2023.R1.2w.S4 | TWCP7-785 | Story | CDS Item Operations Extended | 2023.R1.2w.S4 TWC4618 | 181366 | TWC4618 | Prod migration completed successfully Query view on selected rows returns valid data
<CDS HANA Feature A> - Denodo/APIGee Prod Migration | 1 | cheahchr | seanyitl | 2023.R1.2w.S4 | TWCP7-785 | Story | CDS Item Operations | 2023.R1.2w.S4 TWC3149 | 181707 | TWC3149 | Prod migration completed successfully Query API returns valid data

## lookup
sprint_name | sprint_id | Project Name | Project Key | sprint
2022.R2.2w.S1 TWC3149 | 147205 | CDS Item Operations | TWC3149 | 2022.R2.2w.S1
2022.R2.2w.S2 TWC3149 | 147207 | CDS Item Operations Extended | TWC4618 | 2022.R2.2w.S2
2022.R2.2w.S3 TWC3149 | 147210 |  |  | 2022.R2.2w.S3
2022.R2.2w.S4 TWC3149 | 147212 |  |  | 2022.R2.2w.S4
2022.R2.2w.S5 TWC3149 | 147214 |  |  | 2022.R2.2w.S5
2022.R2.2w.S6 TWC3149 | 147217 |  |  | 2022.R2.2w.S6
2022.R2.2w.SP TWC3149 | 147220 |  |  | 2022.R2.2w.SP
2022.R3.2w.S1 TWC3149 | 160667 |  |  | 2022.R3.2w.S1
2022.R3.2w.S2 TWC3149 | 160674 |  |  | 2022.R3.2w.S2
2022.R3.2w.S3 TWC3149 | 160720 |  |  | 2022.R3.2w.S3
2022.R3.2w.S4 TWC3149 | 160777 |  |  | 2022.R3.2w.S4
2022.R3.2w.S5 TWC3149 | 160802 |  |  | 2022.R3.2w.S5
2022.R3.2w.S6 TWC3149 | 160839 |  |  | 2022.R3.2w.S6
2022.R3.2w.SP TWC3149 | 160854 |  |  | 2022.R3.2w.SP
2022.R4.2w.S1 TWC3149 | 169863 |  |  | 2022.R4.2w.S1
2022.R4.2w.S2 TWC3149 | 169871 |  |  | 2022.R4.2w.S2
2022.R4.2w.S3 TWC3149 | 169887 |  |  | 2022.R4.2w.S3
2022.R4.2w.S4 TWC3149 | 169902 |  |  | 2022.R4.2w.S4
2022.R4.2w.S5 TWC3149 | 169918 |  |  | 2022.R4.2w.S5
2022.R4.2w.S6 TWC3149 | 169929 |  |  | 2022.R4.2w.S6
2022.R4.2w.SP TWC3149 | 169938 |  |  | 2022.R4.2w.SP
2023.R1.2w.S1 TWC3149 | 181686 |  |  | 2023.R1.2w.S1
2023.R1.2w.S2 TWC3149 | 181695 |  |  | 2023.R1.2w.S2
2023.R1.2w.S3 TWC3149 | 181705 |  |  | 2023.R1.2w.S3
2023.R1.2w.S4 TWC3149 | 181707 |  |  | 2023.R1.2w.S4
2023.R1.2w.S5 TWC3149 | 181710 |  |  | 2023.R1.2w.S5
2023.R1.2w.S6 TWC3149 | 181722 |  |  | 2023.R1.2w.S6
2023.R1.2w.SP TWC3149 | 181734 |  |  | 2023.R1.2w.SP
2022.R2.2w.SP TWC4618 | 178762
2022.R3.2w.S1 TWC4618 | 178763
2022.R3.2w.S2 TWC4618 | 178764
2022.R3.2w.S3 TWC4618 | 178765
2022.R3.2w.S4 TWC4618 | 178766
2022.R3.2w.S5 TWC4618 | 178767
2022.R3.2w.S6 TWC4618 | 178768
2022.R3.2w.SP TWC4618 | 178769
2022.R4.2w.S1 TWC4618 | 178770
2022.R4.2w.S2 TWC4618 | 178771
2022.R4.2w.S3 TWC4618 | 178772
2022.R4.2w.S4 TWC4618 | 178773
2022.R4.2w.S5 TWC4618 | 178774
2022.R4.2w.S6 TWC4618 | 178775
2022.R4.2w.SP TWC4618 | 178776
2023.R1.2w.S1 TWC4618 | 181341
2023.R1.2w.S2 TWC4618 | 181346
2023.R1.2w.S3 TWC4618 | 181352
2023.R1.2w.S4 TWC4618 | 181366
2023.R1.2w.S5 TWC4618 | 181398
2023.R1.2w.S6 TWC4618 | 181421
2023.R1.2w.SP TWC4618 | 181478

## HANA AC
Work | Acceptance Criteria
<CDS HANA Feature A> - Requirement | Finalize LDM with DA Complete PDM readiness
<CDS HANA Feature A> - Create Mapping Document, PDM and Wiki | Complete Mapping document, technical design, PDM, WIKI, test plan
<CDS HANA Feature A> - DS Job Technical Design | Complete ETL design document
<CDS HANA Feature A> - DS Job Development | DS job setup and tested running successfully Source tables visible in HANA New tables created
<CDS HANA Feature A> - DS Job Review and Testing | DS job setup and tested running successfully Source tables visible in HANA New tables created
<CDS HANA Feature A> - DS Job QA Migration | QA migration completed successfully
<CDS HANA Feature A> - HANA View Development | A,B,C,D view created/updated as per design document Validate changes made not impacting other views Query view on selected rows returns valid data
<CDS HANA Feature A> - HANA QA Migration | QA migration completed successfully Query view on selected rows returns valid data
<CDS HANA Feature A> - HANA QA Code Review | HANA Code developed as per IT standard
<CDS HANA Feature A> - Batch Job Creation - QA | Batch run successfully Query view on refreshed rows returns valid data
<CDS HANA Feature A> - HANA QA Functional Testing | New/updated features work as per specification without impacting existing business scenario. Test cases and results documented and tracked in JIRA
<CDS HANA Feature A> - Denodo/APIGee development | Complete API development and unit testing
<CDS HANA Feature A> - Denodo/APIGee QA Migration | QA migration completed successfully Query API returns valid data
<CDS HANA Feature A> - DS Job Prod Migration | Prod migration completed successfully Query view on refreshed rows returns valid data
<CDS HANA Feature A> - Batch Job Creation - Prod | Batch run successfully Query view on refreshed rows returns valid data
<CDS HANA Feature A> - HANA Prod Migration | Prod migration completed successfully Query view on selected rows returns valid data
<CDS HANA Feature A> - Denodo/APIGee Prod Migration | Prod migration completed successfully Query API returns valid data

## IBDS1 AC
Work | Acceptance Criteria
<CDS IBDS1.0 Feature A> - Requirement (Technical Design & Test Plan) | Finalize LDM with DA Complete PDM readiness
<CDS IBDS1.0 Feature A> - Create PDM and Wiki | Mapping document, technical design, PDM, WIKI, test plan published and reviewed
<CDS IBDS1.0 Feature A> - ETL Configuration - Dev | ETL run sccessfully without error
<CDS IBDS1.0 Feature A> - ETL Configuration - QA | ETL run sccessfully without error
<CDS IBDS1.0 Feature A> - DB Development | DB development completed and tested without error
<CDS IBDS1.0 Feature A> - DB QA migration | QA migration completed successfully Query view on selected rows returns valid data
<CDS IBDS1.0 Feature A> - Mulesoft Development | API development completed and tested without error
<CDS IBDS1.0 Feature A> - Mulesoft QA Migration | QA migration completed successfully Query API returns valid data
<CDS IBDS1.0 Feature A> - Denodo/APIGee Development | Complete API development and unit testing
<CDS IBDS1.0 Feature A> - Denodo/APIGee QA Migration | QA migration completed successfully Query API returns valid data
<CDS IBDS1.0 Feature A> - Dev Functional Testing | Complete functional testing with sample data
<CDS IBDS1.0 Feature A> - Batch Job Creation - Dev | Batch job run successfully Query view on refreshed rows returns valid data
<CDS IBDS1.0 Feature A> - Batch Job Creation - QA | Batch job run successfully Query view on refreshed rows returns valid data
<CDS IBDS1.0 Feature A> - QA Functional Testing | New/updated features work as per specification without impacting existing business scenario. Test cases and results documented and tracked in JIRA
<CDS IBDS1.0 Feature A> - DB Prod Migration | Prod migration completed successfully Query view on selected rows returns valid data
<CDS IBDS1.0 Feature A> - Mulesoft Prod Migration | Prod migration completed successfully Query API returns valid data
<CDS IBDS1.0 Feature A> - Denodo/APIGee Prod Migration | QA migration completed successfully Query API returns valid data
<CDS IBDS1.0 Feature A> - ETL Configuration - Prod | ETL run sccessfully without error
<CDS IBDS1.0 Feature A> - Batch Job Creation - Prod | Batch job run successfully Query view on refreshed rows returns valid data

## Artifacts Location
Development Standards | URL
Data Modelling standard | Enterprise Data Architecture & Data Modeling Standards - IT Standards - Intel Enterprise Wiki
Data Modelling Tool - ER Studio wiki | https://wiki.ith.intel.com/display/ERStudio/ERStudio+Wiki
ER Studio AGS | https://wiki.ith.intel.com/display/ERStudio/Access+to+ERStudio+using+AGS?src=contextnavpagetreemode
HANA Development Network | Enterprise Developer - SAP HANA - Enterprise Application Developer Network - Intel Enterprise Wiki
API Management (APIGee) | https://wiki.ith.intel.com/display/APIManagement/API+Management+Home
Artifacts
Design Documents | https://intel.sharepoint.com/:f:/r/sites/dnacdsgaritemoperations-PDMHANA/Shared%20Documents/PDM%20HANA/Design%20Document?csf=1&web=1&e=RHIcLb
Test cases & results | https://intel.sharepoint.com/:f:/r/sites/dnacdsgaritemoperations-PDMHANA/Shared%20Documents/PDM%20HANA/Test%20Cases%20and%20Result%20Documents?csf=1&web=1&e=Ueb1wm
API Wiki | Bill Of Material Long Range Planning Details V1 - Enterprise DaaS - Intel Enterprise Wiki